## Sheet1
	Project Start Date:		26-Sep-2022				2022					2023
	Project Name:		Applicability of DSbD to Performance Sensitive Networking Applications				Sep	Oct					Nov				Dec				Jan					Feb				Mar				Apr
				26	3	10	17	24	31	7	14	21	28	5	12	19	26	2	9	16	23	30	6	13	20	27	6	13	20	27	3	10	17
#	Task	Task Type	Start Date	End Date	Work Days	Progress (%)
1	Research	Parent Task	03-Oct-2022	28-Oct-2022	20	100%
1.1	Fundamental CHERI Concepts	Sub-Task	03-Oct-2022	07-Oct-2022	5	100%		u
1.2	C Programming Language	Sub-Task	10-Oct-2022	21-Oct-2022	10	100%				u
1.3	CHERI C/C++ Style Guide	Sub-Task	24-Oct-2022	28-Oct-2022	5	100%					u
2	Setup	Parent Task	03-Oct-2022	14-Oct-2022	10	100%
2.1	Boot Morello Board	Sub-Task	03-Oct-2022	07-Oct-2022	5	100%		u
2.2	Install CheriBSD	Sub-Task	10-Oct-2022	11-Oct-2022	2	100%			u
2.3	Establish Network Connectivity	Sub-Task	12-Oct-2022	14-Oct-2022	3	100%			u
3	Practice Fundamentals	Parent Task	17-Oct-2022	04-Nov-2022	15	100%
3.1	C Tutorials	Sub-Task	17-Oct-2022	21-Oct-2022	5	100%				u
3.2	Vim Tutorial	Sub-Task	24-Oct-2022	25-Oct-2022	2	100%					u
3.3	Create C Applications	Sub-Task	26-Oct-2022	04-Nov-2022	8	100%					u
4	Port DPDK Library	Parent Task	07-Nov-2022	02-Dec-2022	20	100%
4.1	Complete Meson Build	Sub-Task	07-Nov-2022	11-Nov-2022	5	100%					u
4.2	Complete Cross Compilation	Sub-Task	14-Nov-2022	18-Nov-2022	5	100%					u
4.3	Complete Ninja Build	Sub-Task	21-Nov-2022	25-Nov-2022	5	100%					u
4.4	Load Kernel Modules	Sub-Task	28-Nov-2022	02-Dec-2022	5	100%					u
5	Packet Processing Application	Parent Task	05-Dec-2022	27-Jan-2023	40	63%
5.1	Create Packet Streams	Sub-Task	05-Dec-2022	06-Dec-2022	2	100%					u
5.2	Receive Packets	Sub-Task	07-Dec-2022	09-Dec-2022	3	100%					u
5.3	Validate Capability Bounds	Sub-Task	12-Dec-2022	13-Dec-2022	2	100%					u
5.4	Validate Capability Permissions	Sub-Task	14-Dec-2022	16-Dec-2022	3	100%					u
5.5	Dispatch Packets Within Process	Sub-Task	19-Dec-2022	20-Dec-2022	2	100%					u
5.6	Dispatch Packets With Sockets	Sub-Task	21-Dec-2022	23-Dec-2022	3	100%					u
5.7	Create Listener Application	Sub-Task	21-Dec-2022	23-Dec-2022	3	100%					u
5.8	Add Program Operation Mode	Sub-Task	02-Jan-2023	10-Jan-2023	7	50%					u
5.9	Create Packet Consumer	Sub-Task	11-Jan-2023	13-Jan-2023	3	0%					u
5.10	Consume Packets Within Process	Sub-Task	16-Jan-2023	17-Jan-2023	2	0%					u
5.11	Consume Packets In Listener	Sub-Task	18-Jan-2023	20-Jan-2023	3	0%					u
5.12	Classify Packets For Consumers	Sub-Task	23-Jan-2023	27-Jan-2023	5	0%					u
6	Evaluation	Parent Task	30-Jan-2023	17-Feb-2023	15	0%
6.1	Record Performance Metrics	Sub-Task	30-Jan-2023	10-Feb-2023	10	0%					u
6.2	Analyse Results	Sub-Task	13-Feb-2023	17-Feb-2023	5	0%					u
7	Documentation & Assessment	Parent Task	18-Oct-2022	17-Apr-2023	130	67%
7.1	Risks & Unknowns	Sub-Task	18-Oct-2022	18-Oct-2022	1	100%				u
7.2	Health & Safety Form	Sub-Task	24-Oct-2022	24-Oct-2022	1	100%					u
7.3	DSbD Interim Report	Sub-Task	05-Dec-2022	09-Dec-2022	5	100%					u
7.4	QUB Interim Report	Sub-Task	12-Dec-2022	16-Jan-2023	26	100%					u
7.5	Project Demonstration	Milestone	22-Mar-2023	22-Mar-2023	1	0%					u
7.6	QUB Final Report	Sub-Task	20-Feb-2023	17-Apr-2023	41	0%					u
8	Meetings	Parent Task	30-Sep-2022	09-Jan-2023	72	100%
8.1	DSbD Technical Check-In	Milestone	30-Sep-2022	30-Sep-2022	1	100%	u
8.2	Pytilia Project Overview	Milestone	04-Oct-2022	04-Oct-2022	1	100%		u
8.3	Supervisor Meeting	Milestone	11-Oct-2022	11-Oct-2022	1	100%			u
8.4	Supervisor Meeting	Milestone	21-Oct-2022	21-Oct-2022	1	100%				u
8.5	Supervisor Meeting	Milestone	04-Nov-2022	04-Nov-2022	1	100%					u
8.6	DSbD Cohort Check-In	Milestone	04-Nov-2022	04-Nov-2022	1	100%					u
8.7	Supervisor Meeting	Milestone	18-Nov-2022	18-Nov-2022	1	100%					u
8.8	Supervisor Meeting	Milestone	05-Dec-2022	05-Dec-2022	1	100%					u
8.9	Pytilia Check-In	Milestone	06-Dec-2022	06-Dec-2022	1	100%					u
8.10	Supervisor Meeting	Milestone	21-Dec-2022	21-Dec-2022	1	100%					u
8.11	Supervisor Meeting	Milestone	09-Jan-2023	09-Jan-2023	1	100%					u